## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to: | Options
14838 | 17/YH/0405 | 216780 | Adapting individual Cognitive Stimulation Therapy for delivery by a web-application | Yes | 2018-12-13 | 7 | 15 | 22 | 2018-11-15 | 2018-11-21 | 2018-03-09 | 2018-11-21 | 2018-11-28 | N/A | 2018-12-12 | N/A | None | N/A | N/A
143840 | 18/LO/1001 | 246304 | RESTORE-LIFE:A Global PRospective, Multi-cEnter, ObServational post-markeT Study tO assess shoRt, mid and long-term Effectiveness and efficiency of VNS Therapy® as adjunctive therapy in reaL-world patIents with diFficult to treat dEpression. | Yes | 2019-07-04 | 3 | 66 | 69 | 2018-12-20 | 2019-04-26 | 2018-06-13 | 2019-04-28 | 2019-04-29 | N/A | 2019-06-19 | No Patients Consented | Complex referral pathway involving second opinion off-site before intervention can be effected | Neither | N/A
143841 | 15/SC/0606 | 187026 | SYMBAD: Study of Mirtazapine for Agitation in Dementia | Yes | 2019-04-12 | 34 | 10 | 44 | 2019-01-30 | 2019-02-27 | 2016-06-30 | 2019-03-22 | 2019-04-02 | N/A | 2019-04-08 | N/A | None | None | N/A
143842 | 18/WM/0281 | 225736 | Promoting Independence in Dementia (PRIDE): A Feasibility Randomised Controlled Trial | Yes | 2019-04-10 | 16 | 25 | 41 | 2018-10-26 | 2019-02-28 | 2018-10-24 | 2019-03-15 | 2019-03-16 | N/A | 2019-03-18 | N/A | None | None | N/A
143843 | 18/YH/0396 | 250694 | The Cognition and Flow Study: The Effects of Brain Training on Brain Blood Flow | Yes | 2019-02-07 | 25 | 20 | 45 | 2018-12-07 | 2018-12-24 | 2019-01-08 | 2019-01-14 | 2019-01-18 | N/A | 2019-02-06 | N/A | None | N/A | N/A
143849 | 18/LO/0978 | 236277 | Power Up for Parents: A pilot study, promoting parental involvement in shared decision making through technology | Yes | 2019-06-13 | 9 | 20 | 29 | 2019-05-10 | 2019-05-15 | 2018-07-13 | 2019-05-22 | 2019-05-24 | N/A | 2019-05-24 | N/A | None | N/A | N/A
Note on A1: System generated field
Note on G1: Format dd/mm/yyyy. Only available for NHS Permission Submission Type
Note on H1: Format dd/mm/yyyy. Only available for NHS Permission Submission Type
Note on K1: System generated field. Please check your dates if value is negative.
Note on L1: System generated field. Please check your dates if value is negative.
Note on M1: System generated field. Please check your dates if value is negative.
Note on N1: System generated field. Please check your dates if value is negative.
Note on S1: Format dd/mm/yyyy.
Note on T1: Format dd/mm/yyyy.