## Slide 1
Patient and Carer Race Equality Framework (PCREF) & Culture of Care
TRANSFORMATION PROGRAMME FY 25/26
Author: Alison Kirk
Date: 14.04.2025

## Slide 2
Workstream: Workforce and Cultural Awareness
Programme Name: PCREF & Culture of Care
Programme Vision: To improve the access, experiences and outcomes of racialised and ethnically and culturally diverse communities, patients and carers. To improve the culture of inpatient mental health, learning disability and autism wards for patients and staff so that they are safe, therapeutic and equitable places to be cared for, and fulfilling places to work.
Triangle of Care – ensuring that the experiences and needs of racially marginalised carers are meaningfully addressed within PCREF
Use learning from communities to develop up to 3 courses to be delivered via Recovery College
Lived Experience Partners from racialised and ethnically and culturally diverse communities recruited to co-lead implementation of PCREF and Culture of Care programmes
Least Restrictive Practice Group to clinically review restraint use to identify, themes, trends and address areas of improvement
African Heritage Alliance – coproduction and engagement framework
African Heritage Alliance – delivery of community activities to increase awareness of mental health & wellbeing
City East CMHT -Barriers to accessing psychological support mental health project
Identify up to 3 communities to deliver Peer Insights Workshops
Workstream vision statement: Partnership working with racialised and ethnically and culturally diverse communities, leaders, and VCSE organisations.
Workstream vision statement: Ensuring ethnically, and culturally diverse patients and carers are treated as equal partners in decision making on their care and treatment plans, and actively involved in the design, development, and review of care pathways.
Workstream: Partnership Working
Workstream: Coproduction & Lived Experience
Joint Data Quality Metrics with NHFT
Improve recording and demographic data in relation to Complaints and patient experience
understanding health inequalities through a racial lens profiling and benchmarking local population ethnicity data to patient access/DNA data
Review and extend Neighbourhood Data Explorer model to increase geographical ethnicity profiling
Workstream vision statement; Improve data collection and insight around ethnicity and other demographics
Workstream: Improving Data Quality and Insight
Programme Lead: Alison Kirk
Workstream vision statement: A culturally competent and diverse workforce that has a positive impact on patient and carers from racialised and ethnically and culturally diverse communities
Cohort 6 of Reverse Mentoring Programme
Active Bystander Programme
Equality Delivery System (EDS) Domain 2
Implementation of ward-based QI via Culture of Care Programme (Belvoir; Langley and Welford Ward)
CAMHS, develop child focused, culturally appropriate services
Notes: We know….
Appreciate the 3 are different. Work we have done with others is helpful background but our framework helps to frame this
Very different well established but the patient will move between your services so you are connected
Advocate your transformation story
Support you to deliver
Not just about givernance

## Slide 3
Transformation Programme Scorecard
Workstream | Project | ID | At the end of 2025/26 what is the Key Delivery Milestone | Next milestone (This will change during the year as we progress delivery) | Milestone Date | New project (Y/N)
Workforce and Cultural Awareness | Cohort 6 of Reverse Mentoring Programme | 1.1 | Delegates successfully complete the programme providing positive feedback on their Reverse Mentoring For Improvement journey including increased levels of cultural competency. | Midway reflective meeting with mentees | June 2025 | N
 | Active Bystander Programme | 1.2 | Active Bystander Programme Community of Practice established | One day training delivered to 60 LPT staff | Dec 2025 | N
 | Equality Delivery System (EDS) Domain 2 | 1.3 | Grading workshop delivered with key stakeholders demonstrating progress around the implementation plan | Workshop delivered and reflect progress | Jan 2026 | N
 | Implementation of ward-based QI via Culture of Care Programme (Belvoir; Langley and Welford Ward) | 1.4 | Belvoir, Langley and Welford Ward to have implemented change ideas identified | Improvement project updates and progress reports | June 2025 | N
 | CAMHS, Develop child focused, culturally appropriate services | 1.5 | tbc | tbc |  | Y
Partnership Working | African Heritage Alliance – coproduction and engagement framework | 2.1 | Framework for engaging and coproduction with communities to reduce health inequalities in place | Blueprint/report to set out approach and tools for working with marginalised and racialised communities | March 2026 | Y
 | African Heritage Alliance – delivery of community activities to increase awareness of mental health & wellbeing | 2.2 | Community champion/volunteer roles in place to inform communities of early intervention support available | Write up kick off meeting held on 7.5.25 and agree date for community workshop | May 2025 | Y
 | City East CMHT -Barriers to accessing psychological support mental health project | 2.3 | Culturally competent support in place to inform psychological/ early intervention support available | Receive update/progress report on early findings at PCREF Advisory and Design Group | July 20925 | Y
 | Delivery Peer Insights Workshops | 2.4 | Peer Insight Workshops to be delivered in each Neighbourhood | Meet with IMROC and neighbourhood leads, to identify up to three communities to run peer insight workshops | June2025 | Y
We will continue to monthly highlight report overall Transformation delivery to Transformation Quality Improvement Delivery Group

## Slide 4
Transformation Programme Scorecard
Workstream | Project | ID | At the end of 2025/26 what is the Key Delivery Milestone | Next milestone (This will change during the year as we progress delivery) | Milestone Date | New project (Y/N)
Coproduction and Lived Experience | Triangle of Care – participate in national programme to ensuring that the experiences and needs of racially marginalised carers are meaningfully addressed within PCREF | 3.1 | Triangle of Care Assessments undertaken in phase 2 include meeting the needs of racially marginalised carers |  |  | N
 | Use learning from communities to develop up to 3 courses to be delivered via Recovery College | 3.2 | community coproduced courses designed to increase awareness of mental health & wellbeing | Review and findings from community engagement to inform course content for design and delivery | October 2025 | Y
 | Lived Experience Partners from racialised and ethnically and culturally diverse communities recruited to co-lead implementation of PCREF and Culture of Care programmes | 3.3 | A set of Patient Experience Outcome Measures to measure the experience of ethnically and culturally diverse patients and carers at a local level | Establish working group to take work forward | May 2025 | Y
 | The use of restrictive practices could be higher for patients from marginalised and racialised communities | 3.4 | Least Restrictive Practice Group to clinically review restraint use to identify, themes, trends and address areas of improvement | Tbc (MCS) |  | Y
Improve Data Quality & Insight | Data Quality Metrics with NHFT | 4.1 | Quality metrics for PCREF reporting | Group meeting to review questions raised with NHSE in relation to Metric 3 & 5 and SQL used for metrics | May 2025 | N
 | Improve recording and demographic data in relation to Complaints and patient experience | 4.2 | Complainant demographic data regularly collected and reported | Establish working group to include People’s Council members to scope and agree implementation plan | June 2025 | N
 | understanding health inequalities through a racial lens profiling and benchmarking local population ethnicity data to patient access/DNA data | 4.3 | A set of coproduced risk profiles across our communities and services; profiling and benchmarking local population ethnicity data to patient access/DNA data | Demonstrate Risk Profiling Tool at Advisory and Design Group to understand benefits and next steps | May 2025 | Y
 | Review and extend Neighbourhood Data Explorer model to increase geographical ethnicity profiling | 4.4 | Consistency in data sharing across the health and care system | Establish working group to include ICB, Local Authority, VSCE and LPT | June 2025 | Y
We will continue to monthly highlight report overall Transformation delivery to Transformation Quality Improvement Delivery Group

## Slide 5: Transformation Priorities 25/26
Transformation priorities defined as a key area of focus in the delivery of Trust Priorities e.g. Group Strategy (THRIVE) and will make the biggest positive impact on our patient and carer population and staff.
Workforce & Cultural
Awareness
Improve Data Quality
Coproduction and Lived Experience
Partnership Working

## Slide 6
Key Priority | Current position | Aim (SMART) | Expected Impact (Metrics)
Workforce and Cultural Awareness | 2024 staff survey results indicated a rise in the experience of discrimination by Ethnic and cultural Minority staff. "Experience of racism and discrimination" will be a workstream under the OFOW programme. | To improve the experience of ECM staff as reported through the staff survey (WRES indicators 5, 6 and 8). Latter to be specified following workstream meetings with change leaders. | tbc
Coproduction and Lived Experience | Patient Experience is captured through a range of tools and mechanisms across the Trust, but there are gaps in terms of capturing the experiences of those from marginalised or racialised communities. | Agreeing/co-producing with racialised and ethnically and culturally diverse experts by experience which of these access, experience and outcomes measures to monitor routinely. | A suit of measures alongside CQC I Statements which will be used to inform transformation and quality improvement and will be reported to Trust Board
Partnership Working | The Trust currently doesn’t have a framework for engaging and coproducing with racialised and marginalised communities in relation to mental health inequalities | To coproduce, test and design a framework with African Heritage Alliance which can be adopted across racialised and marginalised communities | The Trust will have a robust approach to working, engaging and coproducing with marginalised and racialised communities in relation to tackling health inequalities
Improve Data Quality | Lack of consistency in sharing data across the system to provide robust insight in geographical and ethnicity profiling in relation to mental health inequalities | To have a consistent approach to data sharing and profiling to inform mental health inequalities | Trust and Partners to have robust data/insights into health inequalities aligned to Core 20 plus5 to inform service transformation and coproduction with marginalised and racialised communities.
Transformation Priorities for 25/26
We will ask you for progress at six months (October) and end of year review (March) to showcase the delivery of our Group strategy THRIVE