## WRES Action Plan
Workforce Race Equality Standard 2025/26 | [9 empty] | RAG
Executive Sponsor: Sarah Willis | [9 empty] | Not started
Concerns/not on track
Objective 1: Ensure Recruitment and Selection processes are inclusive. Candidates from ethnic and cultural minority backgrounds have equitable outcomes compared to their white colleagues. | [9 empty] | On track
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG | Complete
1 | Deliver Inclusive (Strength Based) Recruitment Training to all recruiting managers | Head of EDI/Strategic Resourcing Manager | 2025-12-01 | 1. Delivery of training to HR colleagues. 2. Cascaded to recruiting managers. 3. Embedded within L&D offer Continue to monitor diverse panels. | Our Future Our Way - career development workstream Together Against Racism NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metrics 1, 2, 7 Increase in number of people from ethnic and cultural minorities applying for, and being recruited to, roles in LPT. | Ongoing | NHFT inclusive recruitment training delivered to EDI/HR/Recruitment colleagues at LPT. Will work together to create a refreshed, inclusive package for LPT recruiting managers. | Amber
2 | Introduce seen interview questions for job interviews as appropriate | Strategic Resourcing Manager | 2025-12-01 | Development of guidance to be communicated to all recruiting managers | Together Against Racism NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metrics 1 and 2 | Ongoing (mirrors WDES action 7) | Guidance launched. We will monitor the evaluation of this approach via a survey on Jobtrain. | Green
3 | Assess ethnicity pay gap alongside established gender pay gap | EDI Specialist | 2025-10-01 | Analyse 2024/25 pay data to calculate our ethnicity pay gap, and identify hot spots and drivers. Report ECM representation by service where possible. | NHS EDI High Impact Actions: Develop and implement an improvement plan to eliminate pay gaps | Ethnicity pay gap causes identified. | New | Pay gap data being analysed. | Amber
Objective 2: Ensure that staff from ethnic and cultural minorities are benefitting from Talent Management, Succession Planning and Career Progression leading to improvements in progression to senior roles (band 8a and above)
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
4 | Establish Talent Management and succession planning Processes enabling Ethnic and Cultural Minority staff to progress into senior management positions in line with model employer targets, Together Against Racism, and OFOW career development workstream. Progression is not always linked to leadership/management courses, but may be skills-related, exposure-related. | Associate Director of Communications and Head of EDI | 2026-03-01 | Develop talent management plan aligning to LPT, Group, regional and national Talent Management strategies. Launch programme. Create an Inclusive Talent Management toolkit for managers. Assess any inequality in who attends development programmes, e.g. HCSW course. Assess how to identify internal candidates who have applied for several promotions and been unsuccessful, to see what feedback is provided and if there is further work/development/intervention which can be done to aid their career aspirations. Explore how to link development opportunities to the appraisal process on ULearn, to drive succession planning. | Our Future Our Way - career development workstream Together Against Racism NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metrics 1, 2, 4 | Ongoing (mirrors WDES action 9) | ECM Interview Skills sessions are regularly run and have positive feedback. Scoping Careers Advice sessions, run on Teams, as an addition. Targeted ECM We Nurture Programme being delivered. OFOW workstream has commenced and discovery phase includes questions on career development and any barriers to this. Deep dive into DMH recruitment data has commenced, looking at reasons for people being repeatedly unsuccessful at interview; quality of the interview feedback; and any actions that can be taken to improve equity. | Amber
5 | Joint Group action delivering specific, targeted leadership programmes for ECM staff | Head of EDI, Head of OD | 2026-01-01 | Work being scoped to deliver joint LPT/NHFT programmes through the OFOW culture change "Career development" workstream | Our Future Our Way - career development workstream Together Against Racism NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metrics 1, 2, 4 | New | Inclusive Culture and Leadership programme across LLR has inclusive talent management as a key component (ECM Nursing and Midwifery Development Programme, Developing Diverse Leadership). Developing Diverse Senior Leadership Programme (bands 8a to 8c). Programmes now open to non-clinical staff as well. | Blue
Objective 3: Create a culturally inclusive organisation for colleagues from ethnic and cultural minorities
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
6 | Deliver the "Experiences of Racism and Discrimination" workstream of OFOW. | Head of EDI and Head of OD | 2026-05-01 | OD cycle of discovery, design, and delivery phases. | Our Future Our Way - discrimination workstream Together Against Racism | Improvements across metrics 5, 6, 7, 8 | New | Workstream established. Discovery phase includes questions on racism, discrimination, and reporting. | Amber
7 | Launch 7th cohort Reverse Mentoring Programme as a Group with NHFT and continue to grow the community of Active Bystanders | Head of EDI | 2025-11-01 | Launch 7th RM programme as a Group with NHFT Future Active Bystander sessions scheduled. Scope potential for Patient/Lived Experience Partners to be matched to senior staff as reverse mentors, to address health inequalitis and accessibility of services. | NHS EDI High Impact Actions: Chief executives, chairs and board members must have specific and measurable EDI objectives to which they will be individually and collectively accountable | Improvements across metrics 1, 2, 6, 7, 8 Positive feedback from mentors and mentees. | Ongoing | 6th cohort underway of the RM programme. Shortlisted for 2 national awards during 2024. >60 LPT staff trained on ABP. Awareness raising session scheduled for October, and LPT-specific ABP training scheduled for January, to be advertised via EDI groups, HR workforce reports, and ENews. System-wide ABP training is available for LPT staff to book onto in the meantime. | Amber
8 | Create EDI Ambassadors across the Trust | Directorate EDI leads | 2025-10-01 | Create job descriptions and recruit into roles. Provide support and training to EDI ambassadors and connect to Trust wide work. | Our Future Our Way - discrimination workstream Together Against Racism | Improvements in indicators 5,6,7 and 8. | Ongoing | FYPCLDA and CHS have recruited 12 EDI ambassadors. DMH are also reviewing current approaches for adoption of this model. | Amber
9 | Educating staff and line managers on best practice around supporting ECM staff | Directorate EDI leads | Ongoing | Ensure managers are aware of the importance of allowing staff to have protected time to attend network events (1.5 hrs per month) Continue to promote Learning Sets | Our Future Our Way - discrimination workstream Together Against Racism | Improvements in indicators 5,6,7 and 8. | Ongoing | Staff have 1.5 hours of protected time per month to attend staff network events. | Amber
Objective 4: Reduce the amount of bullying, harassment and abuse experienced by colleagues from ethnic and cultural minorities
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
10 | Review Zero Tolerance resources in light of best practice from other Trusts (NE Ambulance Service). | EDI Specialist, Communications | 2025-12-01 | Relaunch of campaign in November 24. Revised resources available and further training offer promoted. Scoping ULearn training. Piloting ZT badges in the community. Will expand this if feedback is positive. Focus on hate crime as a key theme. | NHS EDI High Impact Actions: Create an environment that eliminates the conditions in which bullying, discrimination, harassment and physical violence at work occur. | Improvements in metric 5 Increased number of Ulysses incident reports (as we are aware of under-reporting) but increase in number of incidents with actions recorded to resolve. | Revised (mirrors WDES action 3) | ZT Taskforce co-ordinating ongoing activities. Regular training available to service areas requiring these. New resources developed including videos and posters. Key messages and support being strengthened to ensure that staff feel empowered. Refusal to treat guidance discussed through SLF. ULearn elearning in development, as a resource for managers/staff to be signposted to. Violence & Aggression policy Zero Tolerance section to be strengthened. | Amber
Objective 5: Review disciplinary processes to ensure equity among all colleagues
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
11 | Review disciplinary cases and processes for substantive and bank staff to ensure principles of equity and just culture are embedded at every stage and eliminate disproportionality between ECM and white staff. | HR, EDI | 2025-10-01 | Review processes and themes of disciplinary cases over the year. Present findings to relevant committees and implement any necessary changes. | Together Against Racism NHS EDI High Impact Actions: Create an environment that eliminates the conditions in which bullying, discrimination, harassment and physical violence at work occur | Improvement in indicator 3 (WRES) and indicator 2 (Bank WRES) Reduction in number of disciplinary cases concluded with no case to answer which could have avoided a formal process. | Ongoing | Head of HR has carried out initial review of cases comparing those entering the process to the outcome of each case. Further work required on the past year of cases (2024/25). Data on ER cases goes regularly to PCC. | Amber

## WDES Action Plan
Workforce Disability Equality Standard 2025/26 | [9 empty] | RAG
Executive Sponsor: Sarah Willis | [9 empty] | Not started
Concerns/not on track
Objective 1: To substantially improve the experience of disabled staff of the reasonable adjustments process | [9 empty] | On track
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG | Complete
1 | Embed reasonable adjustments support into day to day practice, by providing managers with the education and support to do this proactively, in clinical and non-clinical roles. | Head of EDI, MAPLE Group, Neurodiversity Group | 2026-01-01 | Oct 24 reasonable adjustments clinics launched. Nov 24 guide launched. Training sessions developed. Training for managers incorporated into Disability Learning Set. Consider a central fund for reasonable adjustments. Survey staff to find out how well the reasonable adjustments process has worked for them. Share case studies of positive reasonable adjustments experiences. MAPLE and Neurodiversity staff networks to consider how staff who are struggling with particular workplace issues may be buddied up with other staff members for support. Assess Staff Survey data to see if there is a difference between clinical and non-clinical staff's satisfaction with reasonable adjustments. Use this to target interventions. | NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity; Develop and implement an improvement plan to eliminate pay gaps; develop a plan to reduce workforce health inequalities. | Improvement in WDES Indicator 8 - The percentages of Disabled colleagues reporting that their employer has made adequate adjustment(s) to enable them to carry out their work from 79% to a target of 90% (80.2% in 24/25). | Revised | Positive impact on WRES Indicator 8 seen in 2024/25. Continue to monitor feedback. Reasonable adjustments clinics continuing with key champions. Support resources completed and shared with staff and managers. MAPLE is organising a Disability History Month event (3/12/25) where a guest speaker will talk about chronic pain. There will also be RA information and resources. | Amber
Objective 2: Create a highly inclusive culture for disabled colleagues so that they have a sense of belonging, feel valued and thrive at LPT
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
2 | Educating staff and line managers on best practice around supporting Disabled staff, approaches to inclusion, and technology. | MAPLE Group, Neurodiversity network Freedom to Speak Up Guardian, Director of HR and Director of MH | 2026-04-01 | Continue to promote MAPLE and Neurodiversity staff networks at induction, Health & Wellbeing Roadshows, through EDI intranet pages, etc. Continue to provide and advertise training and education for staff and/or managers, e.g. on neurodiversity; the redeployment process; reasonable adjustments. Ensure managers know how to access support from Staffside, EDI, Occupational Health, and HR to promote a supportive adjustment/redeployment process where needed, which involves the staff member throughout in decisions about their health and work. Ensure managers are aware of the importance of allowing staff to have protected time to attend network events (1.5 hrs per month).” | NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity; Develop and implement an improvement plan to eliminate pay gaps; develop a plan to reduce workforce health inequalities. | Improvement in metrics 4, 5, 6, 7, 8, 9 Qualitative feedback from listening events | Revised | Staff networks have stand alone budgets to help with promoting their work and activities. Funding has been used to organise Disability History Month and specific training for disabled and ND staff. Psychological Safety definition co-produced with staff networks. EDI, FTSU, Health & Wellbeing, and Staff Engagement have a schedule of site visits throughout Autumn 2025. Leaflets with staff network signup information have been printed and distributed across sites. Videos available for staff and managers to train them on Outlook accessibility, digital accessibility tools, and accessibility software. Ergonomic compuer equipment will be on display as part of the Disability History Month event to raise awareness of the options. | Amber
3 | Review Zero Tolerance resources in light of best practice from other Trusts (NE Ambulance Service). | EDI Specialist, Communications | 2025-12-01 | Relaunch of campaign in November 24. Revised resources available and further training offer promoted. Scoping ULearn training. Piloting ZT badges in the community. Will expand this if feedback is positive. Focus on hate crime as a key theme. | NHS EDI High Impact Actions: Create an environment that eliminates the conditions in which bullying, discrimination, harassment and physical violence at work occur. | Improvements in metric 4 Increased number of Ulysses incident reports (as we are aware of under-reporting) but increase in number of incidents with actions recorded to resolve. | Revised (mirrors WRES action 10) | ZT Taskforce co-ordinating ongoing activities. Regular training available to service areas requiring these. New resources developed including videos and posters being revamped. Key messages and support being strengthened to ensure that staff feel empowered. Refusal to treat guidance discussed through SLF. | Amber
Objective 3: All disabled staff have the confidence to declare their disability on ESR
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
6 | Develop another communication campaign so that staff feel confident sharing their disability on ESR | EDI team | 2025-12-01 | Continue to promote through directorates. Another comms campaign during 2025 Disability History Month (Nov/Dec). Use this as an opportunity to debunk myths about disabilities/abilities. | NHS EDI High Impact Actions: Develop a plan to reduce workforce health inequalities. | Improvement in metrics 1, 7, 9 Increase in % of people sharing their disability status on ESR, closer to the Staff Survey figure of around 27%. | Ongoing | Clear guidance on how to update ESR is available on StaffNet. Comms, guide, and video from Deputy Chair have been shared. Recruitment remind all applicants of the right to request reasonable adjustments, further positioning us as an inclusive employer and encouraging people to tell us their disability status. WDES data suggests some improvement in sharing rates and overall % of workforce with a disability. | Amber
Objective 4: Embed Inclusive recruitment practice towards the employment and retention of candidates with disabilities to guarantee fairness throughout the process.
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
7 | Introduce seen interview questions for job interviews as appropriate | Strategic Resourcing Manager | 2025-12-01 | Development of guidance to be communicated to all recruiting managers | Together Against Racism NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metrics 1 and 2 | Ongoing (mirrors WRES action 2) | Guidance launched. We will monitor the evaluation of this approach via a survey on Jobtrain. | Green
8 | Continue to promote the Trust as a ‘Disability Confident’ employer both internally and via recruitment social media sites | Strategic Resourcing Manager | 2025-12-01 | Review recruitment literature Comms campaign Create page on Jobtrain explaining how we support staff/applicants with disabilities. | Together Against Racism NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metrics 1, 2 and 7. Increase in number of people with disabilities applying for, and being recruited to, roles in LPT. | Ongoing (mirrors WRES action 2) | Recruitment literature includes Disability Confident logo and criteria such as guaranteeing an interview to candidates who meet the minimum criteria. Further work required: specific Comms campaign with volunteers to be featured on social media talking about their positive experiences as a member of staff with a disability/health condition. | Amber
Objective 5: Ensure Career Progression for staff with disabilities through the Talent management and succession planning approach.
No. | Action | Lead | By When | Milestone | Links to Trust strategies and NHS high impact actions | Ambition/Outcomes | New/Ongoing/Revised | Progress | RAG
9 | Establish Talent Management and succession planning Processes enabling Disabled staff to progress into senior management positions in line with OFOW career development workstream. Progression is not always linked to leadership/management courses, but may be skills-related, exposure-related. | Associate Director of Communications and Head of EDI | 2026-03-01 | Develop talent management plan aligning to LPT, Group, regional and national Talent Management strategies. Launch programme. Create an Inclusive Talent Management toolkit for managers. Assess any inequality in who attends development programmes, e.g. HCSW course. Assess how to identify internal candidates who have applied for several promotions and been unsuccessful, to see what feedback is provided and if there is further work/development/intervention which can be done to aid their career aspirations. Explore how to link development opportunities to the appraisal process on ULearn, to drive succession planning. | Our Future Our Way - career development workstream NHS EDI High Impact Actions: Embed fair and inclusive recruitment processes and talent management strategies that target under-representation and lack of diversity | Improvement in metric 1 Increased number of applicants with disabilities applying for LPT roles, particularly at higher bands. | New (mirrors WRES action 4) | Trust wide approach to be developed in line with Our Future Our Way "Career development" Talent Management Workstream for 2025/26. | Amber